## Sheet1
Project Plan - The Gold Standard
Task # | Tasks | Assigned | Pre-Requisites | Planned Completion | Completion Status
1 | Create GitHub Repository | Sawyer |  | 2022-01-31
2 | Exploratory Questions | Group | 1 | 2022-01-31
3 | Napkin Drawing & Feedback | Group | 2 | 2022-02-04
3.1 | Create rough drawings for visualiztions and Dashboard | Group | 2 | 2022-02-02
3.2 | Get and document feedback on drawings visualizations/dashboard | Group | 3.1 | 2022-02-02
3.3 | Update original napkin drawings | Danny | 3.2 | 2022-02-04
3.4 | Note what feedback was/wasn't used and why | Danny | 3.3 | 2022-02-04
4 | ETL Report |  | 3 | 2022-02-11
4.1 | Create Datalake Container and Import Data | Sawyer | 3 | 2022-02-05
4.2 | Create Azure SQL Server Database | Sawyer | 4.1 | 2022-02-06
4.3 | Test Databricks/Kafka Pipeline |  | 4.2 | 2022-02-07
4.4 | Test Skeleton Pipeline from API to Dashboard |  | 4.3 | 2022-02-08
4.5 | Setup Data Factory with Triggers |  | 4.4 | 2022-02-09
4.6 | Research ML Models for Price Regression |  | 4.5 | 2022-02-10
4.7 | Prepare Data for ML Model | Danny | 4.6 | 2022-02-10
4.8 | Implement ML Model |  | 4.7 | 2022-02-10
4.9 | Refine Model and Run |  | 4.8 | 2022-02-11
4.10 | Re-refine Model and Run |  | 4.9 | 2022-02-11
4.11 | Export Python Script |  | 4.10 | 2022-02-11
5 | Dashboard |  | 4 | 2022-02-15
5.1 | Decide Dash or Power Bi | Group | 4 | 2022-02-12
5.2 | Individually pull in dataset and ML model | Everyone indivudally | 5.1 | 2022-02-13
5.3 | Create visualizations on own and note steps | Everyone indivudally | 5.2 | 2022-02-14
5.4 | Create one report using steps each person took to create visualizatons | Group | 5.3 | 2022-02-15
6 | Executive Report |  | 5 | 2022-02-16
6.1 | Introduction/hypothesis/questions |  | 5 | 2022-02-16
6.2 | Research/data gathering/data cleaning/model making |  | 6.1 | 2022-02-16
6.3 | Description/Findings/Visualizations |  | 6.2 | 2022-02-16
6.4 | Conclusion |  | 6.3 | 2022-02-16
7 | Presentation Slides |  | 6 | 2022-02-16
7.1 | Introduction |  | 6 | 2022-02-16
7.2 | Initial Questions |  | 7.1 | 2022-02-16
7.3 | Research Process |  | 7.2 | 2022-02-16
7.4 | Machine Learning |  | 7.3 | 2022-02-16
7.5 | Recommendations |  | 7.4 | 2022-02-16
Last | Presentation Dry Run | Group | EVERYTHING!!!! | 2022-02-17
Last.1 | Figure out who's saying what | Group | EVERYTHING!!!! | 2022-02-17
Last.2 | Make any last minute touchups | Group | EVERYTHING!!!! | 2022-02-17
https://github.com/stuckerdev10/capstone-project-gold-standard